## Sheet1
Introduction: |  | Oibjective of this document is to test the functionality of the main login page.
Test item: |  | UX , API , DB
Feature to be tested: | Approach |  | Testing task | Responsibilities | Schedule | Pass/fail
Login username and password functionality. | Manual testing |  | Enter username and password in the login form | Preet will perform manual testing on UX 1 . | 17 feb'22
Functionality of sign up page and the requirements fo different fields. | Manual testing |  | Click on signup page and try signing up with username and password | Pushti will perform the testing on sign up page and the requirements | 18 feb'22
Link between sign up page and login page after filling out the sign up details | Manual testing |  | After signing up it should navigate to sign in page and should be able to login with new login credentials. | Muhaimin | 19 feb'22
API response | Manual testing with postman software |  | Checking the response code with postman | All the team members will be executing this independently | 20 feb'22
Database | Verification by inspection. |  | Entering user name and password and inspecting the database for that particular entry. | All the team members will be executing this independently | 21 feb'22