## Sheet1
Task Name | Person responsible | Estimated LOE | Due date | Commit
Requirement 1.1 (Landing page shall have link) | Preet | 1-2 Hours | 2022-04-06 | 0520dc8
Requirement 1.2 (Home link) | Preet | 1-2 Hours | 2022-04-06 | 780900a
Requirement 2.1 (Home link will display articl) | Pushti | 2-3 Hours | 2022-04-06 | b0f02a3
Requirement 2.2(article in descending order) | Pushti | 3-4 Hours | 2022-04-06 | b0f02a3
Requirement 3.1(Articles from home link) | Muhaimin | 3-6 Hours | 2022-04-06 | 3da29ed
Requirement 4 | Muhaimin | 2-4 Hours | 2022-04-06 | 3da29ed
Requirement 5 | Pushti | 2-4 Hours | 2022-04-06 | 05c9238
Requirement 6 | Preet | 2-4 Hours | 2022-04-07 | 0520dc8
Requirement 7 | Preet | 2-4 Hours | 2022-04-07 | 0520dc8
Update test plan | Preet,pushti,muhaimin | 1 Hour | 8 - 12 Apr | b33578b
Update test case | Preet,pushti,muhaimin | 1 Hour | 8 - 12 Apr | 0d033f7
Integration testing | Preet,pushti,muhaimin | 3-4 Hours | 8 - 11 Apr | 0d033f7
Sprint 4
Requirement 1 | Preet | 3-4 Hours | 2022-04-16
Requirement 2 | Preet | 3-4 Hours | 2022-04-17
Requirement 3 | Pushti | 3-4 Hours | 2022-04-18
Requirement 4 | Pushti | 3-4 Hours | 2022-04-19
Requirement 5 | Muhaimin | 3-4 Hours | 2022-04-20
Update test case | Preet,pushti,muhaimin | 1 Hour | 21-24 Apr
Update test plan | Preet,pushti,muhaimin | 1 Hour | 21-24 Apr
System testing | Preet,pushti,muhaimin | 5-6 Hour | 21-24 Apr